## Sheet1
| Rosenberg | Rutherford | Anderson | White | Kimmons | Nguyen | Undergrads
June 2020
Manual Website/Social Data Collection
Refine Collection Methods
Develop policy coding scheme
Supervise Undergraduates
Engage w/AB re: Research Plan
July 2020-August 2020
Apply Refined Collection Methods
Continue to Refine Data Collection Methods
Develop AI Text Policy Coding
Manual Website/Social Data Collection
Supervise Undergraduates
Release Initial Data
September 2020-December 2020
Apply Refined Collection Methods
Apply AI Text Policy Coding
Refine Data Visualization Tools
Release Refined Datasets and Tools
January 2021-March 2021
Develop Community-Level Measures
Refine Data Visualization Tools
Construct District Summary Sheets
Validate Summary Sheets
Release Initial Community Datasets
Preregister Aim 2 RQ Methods
Engage w/AB re: Results to Date
April 2021-June 2021
Conduct Aim 2 Analyses
Release Final Datasets and Tools
Submit Scholarly Manuscripts